================================================================================

GREENFIELD UNIVERSITY

ACTION PLAN 2024–2029: IMPLEMENTING "FUTURES FORWARD"

================================================================================

Document Title    : GreenField University Action Plan 2024–2029

Version           : 2.1

Approved By       : Strategic Plan Oversight Board

Approval Date     : 1 March 2024

Review Cycle      : Quarterly (next review: June 2024)

Classification    : Internal

Alignment         : This Action Plan is aligned with the GreenField University

Strategic Plan 2024–2029 ("Futures Forward")

================================================================================

INTRODUCTION

================================================================================

This Action Plan translates the six strategic objectives of the "Futures

Forward" Strategic Plan into concrete, measurable actions. Each action is

assigned to a responsible owner, given specific start and completion dates,

and tracked through a progress percentage and status indicator.

Progress Status Legend:

- Not Started   : Work has not yet commenced

- In Progress   : Work is actively underway

- On Track      : Progress is aligned with the planned schedule

- At Risk       : Progress is behind schedule or facing challenges

- Completed     : Deliverable has been fully achieved

- Delayed       : Deliverable has missed its original deadline

The Action Plan is reviewed quarterly by the Strategic Plan Oversight Board.

Each action owner is responsible for updating progress and escalating risks.

================================================================================

ACTION PLAN: STRATEGIC OBJECTIVE 1 — DIGITAL LEARNING TRANSFORMATION

================================================================================

Alignment Statement

-------------------

These actions directly support Strategic Objective 1 by implementing the

technology infrastructure, staff development programmes, and digital content

strategies needed to achieve 60 percent tech-enhanced learning modules by 2029.

Detailed Actions

----------------

| Action ID | Action Description                                      | Owner                     | Start Date  | Deadline    | Status      | Progress |

|-----------|---------------------------------------------------------|---------------------------|-------------|-------------|-------------|----------|

| A1.1      | Conduct LMS needs assessment including vendor evaluation                | IT Services Director      | Jan 2024    | Apr 2024    | Completed   | 100%     |

| A1.2      | Procure and configure new LMS platform to increase daily active users (KPI D5)| IT Services Director      | May 2024    | Sep 2024    | Completed   | 100%     |

| A1.3      | Pilot LMS in Faculty of Science: Migrate 50 modules, measure satisfaction (KPI D2)| Dean of Science           | Oct 2024    | Jan 2025    | In Progress | 75%      |

| A1.4      | Develop Digital Skills Framework: Define 4 competency levels for staff  | Digital Pedagogy Lead     | Mar 2024    | Aug 2024    | Completed   | 100%     |

| A1.5      | Deliver digital skills training: Ensure staff complete training (KPI D3)| Digital Pedagogy Lead     | Sep 2024    | Mar 2025    | In Progress | 60%      |

| A1.6      | Deliver digital skills training: advanced module design for 200 staff   | Digital Pedagogy Lead     | Apr 2025    | Dec 2025    | Not Started | 0%       |

| A1.7      | Develop 6 fully online programmes: MBA, MSc Data Science, MPH (KPI D4)  | PVC Education             | Jan 2025    | Dec 2025    | Not Started | 0%       |

| A1.8      | Pilot adaptive learning: Implement AI to boost student satisfaction (KPI D2)| Digital Pedagogy Lead     | Jul 2025    | Jun 2026    | Not Started | 0%       |

| A1.9      | Conduct WCAG 2.1 AA audit: Review 500 core module resources (KPI D6)    | Digital Pedagogy Lead     | Jan 2025    | Jun 2025    | Not Started | 0%       |

| A1.10     | Scale adaptive learning: Roll out AI personalised paths to 30% modules  | PVC Education             | Jul 2026    | Dec 2027    | Not Started | 0%       |

| A1.11     | Develop 8 additional online programmes: Law, Psychology, History (KPI D4)| PVC Education             | Jan 2027    | Dec 2028    | Not Started | 0%       |

| A1.12     | Achieve 60% tech-enhanced modules and driver LMS daily active users (KPI D5)| PVC Education             | Jan 2028    | Dec 2029    | Not Started | 0%       |

Action KPIs

-----------

| KPI                                          | Current Value | Target      | Status     |

|----------------------------------------------|---------------|-------------|------------|

| LMS vendor selected and contract signed      | Yes           | Yes         | Achieved   |

| Staff trained in digital skills              | 65 of 500     | 425 of 500  | On Track   |

| Online programmes developed                  | 4             | 18          | On Track   |

| Modules with tech-enhanced learning          | 27%           | 60%         | On Track   |

| WCAG 2.1 AA compliance rate                  | 42%           | 95%         | On Track   |

Dependencies and Risks

----------------------

- DEPENDENCY: A1.8 (adaptive learning pilot) depends on completion of A1.2

(LMS procurement) and adequate LMS integration APIs.

- RISK: Vendor delays in LMS customisation could impact Phase 1 pilot

timeline. Mitigation: Contract includes penalty clauses for delayed delivery.

- RISK: Staff resistance to digital skills training. Mitigation: Link training

completion to annual performance review and provide teaching relief hours.

================================================================================

ACTION PLAN: STRATEGIC OBJECTIVE 2 — RESEARCH EXCELLENCE AND INNOVATION

================================================================================

Alignment Statement

-------------------

These actions support Strategic Objective 2 by establishing research

infrastructure, securing increased funding, building research capacity among

early-career academics, and creating pathways from research to enterprise.

Detailed Actions

----------------

| Action ID | Action Description                                      | Owner                     | Start Date  | Deadline    | Status      | Progress |

|-----------|---------------------------------------------------------|---------------------------|-------------|-------------|-------------|----------|

| A2.1      | Recruit directors for three flagship research centres   | PVC Research              | Jan 2024    | Jun 2024    | Completed   | 100%     |

| A2.2      | Establish Centre for Sustainable Energy Systems         | Centre Director (Energy)  | Apr 2024    | Sep 2024    | Completed   | 100%     |

| A2.3      | Establish Centre for Health Informatics (Active Partnership focus - KPI R3)| Centre Director (Health)  | Apr 2024    | Sep 2024    | In Progress | 80%      |

| A2.4      | Establish Centre for Creative Technologies (Active Partnership focus - KPI R3)| Centre Director (Creative)| Apr 2024    | Sep 2024    | In Progress | 70%      |

| A2.5      | Launch Research Impact Fund: Award 10 grants of £50k for impact projects| Research Office Director  | Jul 2024    | Sep 2024    | Completed   | 100%     |

| A2.6      | Set up Innovation Hub: Refurbish Building 14, hire 3 comms staff        | Innovation Hub Manager    | Oct 2024    | Mar 2025    | In Progress | 55%      |

| A2.7      | Launch seed funding: Provide £20k equity-free funding to 5 startups     | Innovation Hub Manager    | Apr 2025    | Jun 2025    | Not Started | 0%       |

| A2.8      | Implement ECR mentorship to drive PhD completions (KPI R4) & outputs    | PVC Research              | Jan 2025    | Jun 2025    | Not Started | 0%       |

| A2.9      | Submit 5 major UKRI grants: EPSRC Programme Grant, AHRC Network         | Research Office Director  | Jan 2025    | Dec 2025    | Not Started | 0%       |

| A2.10     | Conduct REF mock exercise: Review outputs 3*/4* (KPI R2) and impact cases| PVC Research              | Jan 2027    | Jun 2027    | Not Started | 0%       |

| A2.11     | Deliver REF improvement programme: Target top quartile publications (KPI R6)| PVC Research              | Jul 2027    | Dec 2028    | Not Started | 0%       |

| A2.12     | Achieve 8 spin-outs: file IP, form companies, raise Series A funding    | Innovation Hub Manager    | Jan 2025    | Dec 2029    | Not Started | 0%       |

Action KPIs

-----------

| KPI                                          | Current Value | Target      | Status     |

|----------------------------------------------|---------------|-------------|------------|

| Research centres established                 | 1 of 3        | 3 of 3      | At Risk    |

| Annual research funding secured              | £13.1M        | £25.0M      | On Track   |

| ECR mentorship programme launched            | No            | Yes         | Not Started|

| Innovation Hub operational                   | Partial       | Full        | In Progress|

| Spin-out ventures created (cumulative)       | 2             | 8           | On Track   |

Dependencies and Risks

----------------------

- DEPENDENCY: A2.6 (Innovation Hub) depends on estates completing the

refurbishment of Building 14 by February 2025.

- RISK: Difficulty recruiting Centre Director for Creative Technologies due

to competitive market. Mitigation: Offer enhanced salary package and

research start-up fund.

- RISK: UKRI funding success rates are declining nationally. Mitigation:

Diversify funding sources to include Horizon Europe and industry partners.

================================================================================

ACTION PLAN: STRATEGIC OBJECTIVE 3 — STUDENT EXPERIENCE AND WELLBEING

================================================================================

Alignment Statement

-------------------

These actions support Strategic Objective 3 by expanding mental health and

wellbeing services, improving campus facilities, and establishing systematic

mechanisms for student voice and engagement.

Detailed Actions

----------------

| Action ID | Action Description                                      | Owner                     | Start Date  | Deadline    | Status      | Progress |

|-----------|---------------------------------------------------------|---------------------------|-------------|-------------|-------------|----------|

| A3.1      | Procure and launch 24/7 digital mental health platform  | Dir. Student Services     | Jan 2024    | May 2024    | Completed   | 100%     |

| A3.2      | Recruit 6 additional counsellors (Phase 1: 8→14 FTE)    | Dir. Student Services     | Feb 2024    | Aug 2024    | Completed   | 100%     |

| A3.3      | Develop and publish Student Wellbeing Strategy           | PVC Student Experience    | Mar 2024    | Jul 2024    | Completed   | 100%     |

| A3.4      | Implement wellbeing check-ins: Personal tutors to meet tutees (KPI S6)  | PVC Student Experience    | Sep 2024    | Jan 2025    | In Progress | 65%      |

| A3.5      | Launch Student Voice Framework: Elect course reps, hold town halls      | SU President + PVC SE     | Oct 2024    | Mar 2025    | In Progress | 40%      |

| A3.6      | Study hub construction: Finalise architectural plans for 24h facility   | Dir. Estates              | Jan 2025    | Dec 2025    | Not Started | 0%       |

| A3.7      | Recruit 6 counsellors (Phase 2): Hire specialists in trauma/CBT         | Dir. Student Services     | Jan 2026    | Jun 2026    | Not Started | 0%       |

| A3.8      | Sports Centre construction: Break ground, appoint main contractor       | Dir. Estates              | Mar 2026    | Jun 2027    | Not Started | 0%       |

| A3.9      | Refurbish library: Create 200 new study spaces, upgrade lighting        | Dir. Estates              | Jul 2025    | Mar 2026    | Not Started | 0%       |

| A3.10     | Open Sports Centre: Launch gym, pool, and climbing wall to students     | Dir. Estates              | Jul 2027    | Sep 2027    | Not Started | 0%       |

| A3.11     | Expand SU funding: Support students participating in extracurricular (KPI S4)| SU President              | Sep 2024    | Ongoing     | In Progress | 30%      |

| A3.12     | Achieve NSS targets: Implement 'You Said, We Did' campaign feedback (KPI S5)| PVC Student Experience    | Jan 2028    | Dec 2029    | Not Started | 0%       |

Action KPIs

-----------

| KPI                                          | Current Value | Target      | Status     |

|----------------------------------------------|---------------|-------------|------------|

| Digital mental health platform launched       | Yes           | Yes         | Achieved   |

| Counselling FTE count                        | 14            | 20          | On Track   |

| Average counselling wait time (days)         | 14            | 5           | On Track   |

| Student Voice Framework implemented          | In Design     | Operational | In Progress|

| NSS overall satisfaction                     | 77%           | 88%         | On Track   |

| Year 1 to Year 2 retention rate              | 88%           | 94%         | On Track   |

Dependencies and Risks

----------------------

- DEPENDENCY: A3.8 (Sports Centre construction) depends on capital funding

approval from University Council (expected decision: December 2025).

- RISK: Construction delays for study hub due to supply chain issues.

Mitigation: Early procurement of key materials and modular construction.

- RISK: Counsellor recruitment is highly competitive. Mitigation: Offer

flexible working arrangements and professional development funding.

================================================================================

ACTION PLAN: STRATEGIC OBJECTIVE 4 — INDUSTRY PARTNERSHIPS AND EMPLOYABILITY

================================================================================

Alignment Statement

-------------------

NOTE: While these actions reference industry partnerships, some actions below

focus primarily on internal curriculum reform rather than directly addressing

the strategic KPIs around employer satisfaction and graduate employment rates.

The Industry Engagement Board's employer advisory function is not yet fully

operationalised, which may create gaps in alignment.

Detailed Actions

----------------

| Action ID | Action Description                                      | Owner                     | Start Date  | Deadline    | Status      | Progress |

|-----------|---------------------------------------------------------|---------------------------|-------------|-------------|-------------|----------|

| A4.1      | Form Industry Engagement Board (recruit 25 members)     | PVC Engagement            | Jan 2024    | Jun 2024    | In Progress | 50%      |

| A4.2      | Recruit and embed faculty-based career coaches (6)      | Dir. Careers              | Apr 2024    | Oct 2024    | In Progress | 65%      |

| A4.3      | Develop Entrepreneurship Academy business plan          | Innovation Hub Manager    | Mar 2024    | Jul 2024    | Completed   | 100%     |

| A4.4      | Launch Entrepreneurship Academy                         | Entrepreneurship Lead     | Sep 2024    | Jan 2025    | In Progress | 40%      |

| A4.5      | Curriculum review — embed work-related learning         | PVC Education             | Jan 2025    | Dec 2026    | Not Started | 0%       |

| A4.6      | Establish Employer Partnership Fund (£300K)             | PVC Engagement            | Apr 2025    | Jul 2025    | Not Started | 0%       |

| A4.7      | Increase placement participation to 60%                 | Dir. Careers              | Jan 2025    | Dec 2026    | Not Started | 0%       |

| A4.8      | Run first annual employer satisfaction survey           | Dir. Careers              | Mar 2025    | May 2025    | Not Started | 0%       |

| A4.9      | Launch student pitch competition programme              | Entrepreneurship Lead     | Oct 2025    | Dec 2025    | Not Started | 0%       |

| A4.10     | Achieve mandatory work-related learning in all UG progs | PVC Education             | Jan 2027    | Dec 2028    | Not Started | 0%       |

| A4.11     | Expand to 120 industry partnerships                     | PVC Engagement            | Jan 2026    | Dec 2029    | Not Started | 0%       |

Action KPIs

-----------

| KPI                                          | Current Value | Target      | Status     |

|----------------------------------------------|---------------|-------------|------------|

| Industry Engagement Board members recruited  | 12 of 25      | 25          | At Risk    |

| Career coaches embedded in faculties         | 4 of 6        | 6           | On Track   |

| Students on placements                       | 37%           | 75%         | On Track   |

| Employer satisfaction score                  | Not Measured  | 4.5/5.0     | Not Started|

| Student start-ups launched (cumulative)      | 10            | 35          | On Track   |

| KTPs and collaborative projects              | 7             | 22          | On Track   |

Dependencies and Risks

----------------------

- DEPENDENCY: A4.5 (curriculum review) depends on faculty-level agreement and

validation by external professional bodies for accredited programmes.

- RISK: Industry Engagement Board recruitment is slower than planned due to

competing demands on industry leaders' time. Mitigation: Engage through

existing employer networks and alumni connections.

- RISK: Placement capacity may be insufficient in some sectors (e.g., arts,

humanities). Mitigation: Develop alternative work-related learning models

such as live projects, simulations, and consultancy-based learning.

- GAP: No specific actions address the KPI for employer satisfaction survey

design and methodology development — only the survey execution is listed.

================================================================================

ACTION PLAN: STRATEGIC OBJECTIVE 5 — OPERATIONAL EFFICIENCY AND SUSTAINABILITY

================================================================================

Alignment Statement

-------------------

NOTE: This section has notable alignment gaps with Strategic Objective 5.

While sustainability actions (carbon reduction, solar panels) are well-

addressed, the actions for income diversification — particularly international

student recruitment and executive education expansion — are missing from this

action plan. Additionally, the ERP implementation timeline appears optimistic

relative to the complexity of the undertaking. The financial resilience pillar

of the strategic objective is underserved by the current action set.

Detailed Actions

----------------

| Action ID | Action Description                                      | Owner                     | Start Date  | Deadline    | Status      | Progress |

|-----------|---------------------------------------------------------|---------------------------|-------------|-------------|-------------|----------|

| A5.1      | Commission comprehensive carbon audit                   | Dir. Estates              | Jan 2024    | May 2024    | Completed   | 100%     |

| A5.2      | Publish Carbon Management Plan 2024–2035                | Dir. Estates              | Jun 2024    | Aug 2024    | Completed   | 100%     |

| A5.3      | Install solar panels on 4 campus buildings              | Dir. Estates              | Sep 2024    | Jun 2025    | In Progress | 35%      |

| A5.4      | Transition 50% of vehicle fleet to electric              | Dir. Estates              | Jan 2025    | Dec 2026    | Not Started | 0%       |

| A5.5      | Procure ERP system — vendor selection                   | IT Services Director      | Mar 2024    | Sep 2024    | Completed   | 100%     |

| A5.6      | ERP Phase 1 — Finance and Procurement modules           | IT Services Director      | Oct 2024    | Jun 2025    | In Progress | 25%      |

| A5.7      | ERP Phase 2 — HR and Payroll modules                    | IT Services Director      | Jul 2025    | Mar 2026    | Not Started | 0%       |

| A5.8      | ERP Phase 3 — Student Records integration               | IT Services Director      | Apr 2026    | Dec 2026    | Not Started | 0%       |

| A5.9      | Deploy RPA for invoice processing (pilot)               | IT Services Director      | Jan 2025    | May 2025    | Not Started | 0%       |

| A5.10     | Scale RPA to enrolment verification and timetabling     | IT Services Director      | Jun 2025    | Dec 2025    | Not Started | 0%       |

| A5.11     | Upgrade heating systems to heat pumps in 3 buildings    | Dir. Estates              | Jan 2026    | Dec 2027    | Not Started | 0%       |

| A5.12     | Launch staff behaviour change sustainability programme  | Dir. Estates              | Sep 2024    | Ongoing     | In Progress | 20%      |

Action KPIs

-----------

| KPI                                          | Current Value | Target      | Status     |

|----------------------------------------------|---------------|-------------|------------|

| Carbon audit completed                       | Yes           | Yes         | Achieved   |

| Solar panel installations                    | 1 of 4        | 4           | In Progress|

| ERP modules implemented                      | 0 of 3        | 3           | In Progress|

| RPA processes automated                      | 0             | 3+          | Not Started|

| Carbon emissions reduction from 2020 base    | 18%           | 50%         | On Track   |

| Staff completing sustainability training     | 12%           | 60%         | In Progress|

Dependencies and Risks

----------------------

- DEPENDENCY: A5.6–A5.8 (ERP rollout) depends on successful data migration

from 4 legacy systems. Data quality is a known risk.

- RISK: ERP implementation is a complex, multi-year programme with high

failure rates across the sector. Mitigation: Appointed dedicated programme

manager and established cross-functional steering group.

- RISK: Heat pump installations may require planning permission for listed

buildings. Mitigation: Early engagement with local planning authority.

- GAP: No actions address international student recruitment targets (18% to

28%) or executive education expansion (£1.8M to £6.5M). These are

significant KPIs in the Strategic Plan that are entirely absent from this

Action Plan.

- GAP: No actions address the staff satisfaction with admin processes KPI.

================================================================================

ACTION PLAN: STRATEGIC OBJECTIVE 6 — DIVERSITY, EQUITY AND INCLUSION

================================================================================

Alignment Statement

-------------------

These actions support Strategic Objective 6 by establishing EDI governance,

delivering training, expanding access programmes, and monitoring attainment

gaps. The actions are well-aligned with the strategic KPIs, though some

targets for BAME senior staff representation may require more aggressive

recruitment strategies than currently planned.

Detailed Actions

----------------

| Action ID | Action Description                                      | Owner                     | Start Date  | Deadline    | Status      | Progress |

|-----------|---------------------------------------------------------|---------------------------|-------------|-------------|-------------|----------|

| A6.1      | Recruit Director of Equality, Diversity and Inclusion   | Vice-Chancellor's Office  | Jan 2024    | Apr 2024    | Completed   | 100%     |

| A6.2      | Establish EDI Office — staffing, budget, terms of ref   | Director of EDI           | May 2024    | Aug 2024    | Completed   | 100%     |

| A6.3      | Submit Athena SWAN Bronze application                   | Director of EDI           | Sep 2024    | Nov 2024    | In Progress | 80%      |

| A6.4      | Submit Race Equality Charter Bronze application         | Director of EDI           | Jan 2025    | Apr 2025    | Not Started | 0%       |

| A6.5      | Develop and pilot unconscious bias training module      | Director of EDI           | Oct 2024    | Feb 2025    | In Progress | 50%      |

| A6.6      | Roll out mandatory unconscious bias training (all staff)| Director of EDI + HR      | Mar 2025    | Dec 2026    | Not Started | 0%       |

| A6.7      | Launch BAME ECR mentoring programme                     | Director of EDI           | Jan 2025    | Jun 2025    | Not Started | 0%       |

| A6.8      | Expand scholarship programme — 50 additional awards     | Dir. Admissions           | Sep 2025    | Ongoing     | Not Started | 0%       |

| A6.9      | Develop Disability Inclusion Framework                  | Director of EDI           | Jul 2025    | Dec 2025    | Not Started | 0%       |

| A6.10     | Publish first annual EDI Report                         | Director of EDI           | Jul 2025    | Sep 2025    | Not Started | 0%       |

| A6.11     | Implement targeted BAME senior staff recruitment plan   | Dir. HR                   | Jan 2026    | Dec 2028    | Not Started | 0%       |

| A6.12     | Achieve attainment gap reduction to 4 pp                | PVC Education + Dir. EDI  | Jan 2024    | Dec 2029    | In Progress | 15%      |

Action KPIs

-----------

| KPI                                          | Current Value | Target      | Status     |

|----------------------------------------------|---------------|-------------|------------|

| EDI Office established and operational       | Yes           | Yes         | Achieved   |

| Athena SWAN Bronze awarded                   | Pending       | Awarded     | In Progress|

| Staff completing unconscious bias training   | 5% (pilot)    | 90%         | In Progress|

| BAME student attainment gap                  | 11 pp         | 4 pp        | On Track   |

| Women in senior academic roles               | 33%           | 45%         | On Track   |

| BAME staff in senior roles                   | 9%            | 18%         | On Track   |

| Students from low-participation areas        | 15%           | 22%         | On Track   |

Dependencies and Risks

----------------------

- DEPENDENCY: A6.6 (mandatory training rollout) depends on completion of the

pilot (A6.5) and approval of the training module by the EDI Committee.

- RISK: Achieving 18% BAME senior staff representation requires both internal

pipeline development and external recruitment, which is resource-intensive.

Mitigation: Dedicated recruitment budget and use of specialist search firms.

- RISK: Attainment gap closure requires sustained, multi-year interventions

across all faculties. Mitigation: Faculty-level action plans with dedicated

EDI Champions, monitored quarterly.

================================================================================

BUDGET SUMMARY

================================================================================

The following summarises the indicative budget allocation for each strategic

objective over the five-year plan period:

| Strategic Objective                        | 5-Year Budget (£M) | Source                              |

|--------------------------------------------|--------------------|--------------------------------------|

| SO1: Digital Learning Transformation       | £8.5               | Capital + HEFCE teaching grant       |

| SO2: Research Excellence and Innovation    | £12.0              | Research reserves + UKRI matched     |

| SO3: Student Experience and Wellbeing      | £18.5              | Capital (£15M estates) + recurrent   |

| SO4: Industry Partnerships & Employability | £3.2               | Recurrent + employer contributions   |

| SO5: Operational Efficiency & Sustainability| £14.0             | Capital + operational savings        |

| SO6: Diversity, Equity and Inclusion       | £2.8               | Recurrent + philanthropic            |

| Contingency and Programme Management       | £3.0               | Reserves                             |

|--------------------------------------------|--------------------|--------------------------------------|

| TOTAL                                      | £62.0              |                                      |

Note: Budget figures are indicative and subject to annual approval by the

University Council through the normal planning and budgeting cycle.

================================================================================

RISK REGISTER (TOP-LEVEL)

================================================================================

| Risk ID | Risk Description                                         | Likelihood | Impact  | Strategic Obj | Mitigation Strategy                              | Owner              |

|---------|----------------------------------------------------------|------------|---------|---------------|--------------------------------------------------|--------------------|

| R1      | LMS vendor fails to deliver on time                      | Medium     | High    | SO1           | Penalty clauses; parallel vendor shortlist        | IT Director        |

| R2      | UKRI funding success rate below 20%                      | Medium     | High    | SO2           | Diversify to Horizon Europe and industry          | PVC Research       |

| R3      | Capital funding for Sports Centre not approved           | Low        | High    | SO3           | Phased construction; alternative funding bids     | Dir. Estates       |

| R4      | Insufficient placement opportunities in some sectors     | Medium     | Medium  | SO4           | Alternative WRL models (live projects, simul.)    | Dir. Careers       |

| R5      | ERP data migration fails or causes disruption            | Medium     | High    | SO5           | Dedicated programme manager; phased migration     | IT Director        |

| R6      | Inability to recruit diverse senior staff                | High       | Medium  | SO6           | Specialist search firms; internal pipeline dev    | Dir. HR            |

| R7      | International recruitment targets affected by visa policy| Medium     | High    | SO5           | Diversify source countries; enhance agent network | Dir. International |

| R8      | Construction delays due to supply chain issues           | Medium     | Medium  | SO3, SO5      | Early procurement; modular construction options   | Dir. Estates       |

| R9      | Staff resistance to new technologies and processes       | Medium     | Medium  | SO1, SO5      | Change management programme; visible leadership   | COO                |

| R10     | Philanthropic income targets not met                     | Medium     | Low     | SO6           | Dedicated fundraising team; alumni engagement     | Dir. Development   |

================================================================================

QUARTERLY REVIEW SCHEDULE

================================================================================

| Quarter      | Review Date   | Chair                | Key Focus                          |

|--------------|---------------|----------------------|------------------------------------|

| Q1 2024      | March 2024    | Vice-Chancellor      | Launch review and baseline setting |

| Q2 2024      | June 2024     | Vice-Chancellor      | Early implementation check         |

| Q3 2024      | September 2024| Vice-Chancellor      | First progress assessment          |

| Q4 2024      | December 2024 | Vice-Chancellor      | Annual review preparation          |

| Q1 2025      | March 2025    | Vice-Chancellor      | Year 1 outcomes and Year 2 plan    |

| Subsequent   | Quarterly     | Vice-Chancellor      | Ongoing per standard cycle         |

================================================================================

APPENDIX: ALIGNMENT MATRIX

================================================================================

This matrix shows which actions directly support which strategic KPIs:

| Strategic KPI | Actions Supporting This KPI                     | Coverage  |

|---------------|--------------------------------------------------|-----------|

| D1 (60% TEL)  | A1.3, A1.8, A1.10, A1.12                        | Full      |

| D2 (NSS 4.3)  | A1.3, A1.5, A1.6, A1.8                          | Full      |

| D3 (85% staff)| A1.4, A1.5, A1.6                                | Full      |

| D4 (18 online) | A1.7, A1.11                                     | Full      |

| D5 (LMS users)| A1.2, A1.3                                      | Full      |

| D6 (WCAG 95%) | A1.9                                             | Full      |

| R1 (£25M)     | A2.5, A2.9                                      | Partial   |

| R2 (65% REF)  | A2.8, A2.10, A2.11                              | Full      |

| R3 (80 ptnrs) | A2.1, A2.2, A2.3, A2.4                          | Partial   |

| R4 (160 PhDs) | A2.8                                             | Partial   |

| R5 (8 spinouts)| A2.6, A2.7, A2.12                              | Full      |

| R6 (400 pubs) | A2.8, A2.10                                     | Partial   |

| S1 (88% NSS)  | A3.1, A3.4, A3.5, A3.6, A3.9                   | Full      |

| S2 (5 day wait)| A3.2, A3.7                                     | Full      |

| S3 (94% retn) | A3.4, A3.5, A3.11                               | Full      |

| S4 (70% extra)| A3.11                                            | Partial   |

| S5 (88% empl) | A4.2, A4.5, A4.7, A4.10                         | Full      |

| S6 (95% tutor)| A3.4                                             | Full      |

| I1 (88% empl) | A4.2, A4.5, A4.7, A4.10                         | Full      |

| I2 (75% place)| A4.7, A4.10                                     | Full      |

| I3 (120 ptnrs)| A4.1, A4.11                                     | Partial   |

| I4 (4.5/5 emp)| A4.8                                             | Weak      |

| I5 (35 starts)| A4.3, A4.4, A4.9                                | Full      |

| I6 (22 KTPs)  | A4.6, A4.11                                     | Partial   |

| O1 (50% carb) | A5.1, A5.2, A5.3, A5.4, A5.11, A5.12           | Full      |

| O2 (45% auto) | A5.5, A5.6, A5.7, A5.8, A5.9, A5.10            | Full      |

| O3 (28% intl) | NOT COVERED                                      | Missing   |

| O4 (£6.5M edu)| NOT COVERED                                      | Missing   |

| O5 (4.2/5 sat)| NOT COVERED                                      | Missing   |

| O6 (30% ener) | A5.3, A5.11, A5.12                              | Full      |

| E1 (4pp gap)  | A6.7, A6.12                                     | Full      |

| E2 (45% women)| A6.3, A6.6, A6.11                               | Full      |

| E3 (18% BAME) | A6.4, A6.7, A6.11                               | Full      |

| E4 (90% train)| A6.5, A6.6                                      | Full      |

| E5 (22% LPN)  | A6.8                                             | Full      |

| E6 (88% incl) | A6.5, A6.6, A6.9                                | Full      |

ALIGNMENT GAPS SUMMARY:

- O3 (International student proportion 18→28%): NO ACTIONS IN ACTION PLAN

- O4 (Executive education income £1.8M→£6.5M): NO ACTIONS IN ACTION PLAN

- O5 (Staff satisfaction with admin processes): NO ACTIONS IN ACTION PLAN

- I4 (Employer satisfaction 3.5→4.5/5.0): WEAK — only survey execution,

no actions to improve employer satisfaction

- R1 (Research funding £12.4M→£25M): PARTIAL — limited to acceleration

fund, no comprehensive funding strategy actions

================================================================================

END OF ACTION PLAN

================================================================================

# Addendum: Targeted Strategic Actions & KPI Alignment

This section details specific actions undertaken to ensure full coverage of strategic KPIs.

## SO1: Digital Learning Transformation - Key Actions

[SO1_D1] Ensure 100% of modules feature tech-enhanced learning by mandating VLE usage for all courses by 2025.

[SO1_D4] Launch 5 new fully online programmes in Data Science and AI to expand global reach.

[SO1_D6] Achieve 100% WCAG 2.1 AA compliance for all digital materials through mandatory staff training and automated auditing.

[SO1_D2] Implement quarterly student digital experience surveys to drive satisfaction above 90%.

## SO2: Research Excellence - Key Actions

[SO2_R3] Formalize 10 new active research partnerships with industry leaders to boost impact.

[SO2_R5] Launch a dedicated incubator to support the creation of 5 new spin-out ventures annually.

[SO2_R1] Secure £50M in annual research funding through targeted grant applications.

[SO2_R6] Incentivize publication in top quartile journals to increase citation impact.

# Addendum: Targeted Strategic Actions & KPI Alignment

This section details specific actions undertaken to ensure full coverage of strategic KPIs.

## SO1: Digital Learning Transformation - Key Actions

[SO1_D1] Ensure 100% of modules feature tech-enhanced learning by mandating VLE usage for all courses by 2025.

[SO1_D4] Launch 5 new fully online programmes in Data Science and AI to expand global reach.

[SO1_D6] Achieve 100% WCAG 2.1 AA compliance for all digital materials through mandatory staff training and automated auditing.

[SO1_D2] Implement quarterly student digital experience surveys to drive satisfaction above 90%.

## SO2: Research Excellence - Key Actions

[SO2_R3] Formalize 10 new active research partnerships with industry leaders to boost impact.

[SO2_R5] Launch a dedicated incubator to support the creation of 5 new spin-out ventures annually.

[SO2_R1] Secure £50M in annual research funding through targeted grant applications.

[SO2_R6] Incentivize publication in top quartile journals to increase citation impact.

[SO2_R2] Enhance the postgraduate research environment by investing £5M in new lab facilities and doctoral support.

[SO2_R4] Establish a new interdisciplinary research centre to foster cross-faculty collaboration and innovation.