================================================================================

GREENFIELD UNIVERSITY

STRATEGIC PLAN 2024–2029: "FUTURES FORWARD"

================================================================================

Document Title    : GreenField University Strategic Plan 2024–2029

Version           : 2.1

Approved By       : University Council

Approval Date     : 15 January 2024

Review Cycle      : Annual (next review: January 2025)

Classification    : Public

================================================================================

EXECUTIVE SUMMARY

================================================================================

GreenField University is a mid-sized public university located in Bristol,

United Kingdom, serving approximately 18,000 students across six faculties.

Founded in 1962, the university has built a reputation for applied research,

community engagement, and widening participation. However, the rapidly changing

higher education landscape — driven by digital transformation, shifting student

expectations, evolving employer needs, and global sustainability challenges —

demands a bold, forward-looking strategic vision.

"Futures Forward" is a five-year strategic plan designed to position GreenField

University as a leader in technology-enhanced learning, impactful research, and

inclusive education. The plan sets out six strategic objectives, each with

measurable key performance indicators (KPIs), clear timelines, and defined

accountability structures.

VISION:

To be a globally connected university that transforms lives through innovative

education, pioneering research, and sustainable community impact.

MISSION:

GreenField University empowers students, staff, and communities to thrive

through inclusive learning, discovery, and engagement. We combine academic

rigour with real-world relevance to prepare graduates who shape a better future.

CORE VALUES:

1. Innovation        — Embracing new ideas and technologies

2. Inclusivity       — Ensuring equal access and opportunity for all

3. Integrity         — Upholding ethical standards in all activities

4. Impact            — Delivering measurable outcomes for society

5. Collaboration     — Partnering across disciplines and borders

6. Sustainability    — Acting responsibly toward the environment and society

================================================================================

STRATEGIC OBJECTIVE 1: DIGITAL LEARNING TRANSFORMATION

================================================================================

Description

-----------

GreenField University recognises that digital technologies are reshaping how

students learn, how educators teach, and how institutions operate. This

objective focuses on embedding digital tools, platforms, and pedagogies across

all programmes to create a flexible, personalised, and engaging learning

experience.

The university will invest in a next-generation Learning Management System

(LMS), develop AI-assisted tutoring capabilities, create a digital skills

framework for all staff, and expand the portfolio of fully online and blended

programmes. By 2029, at least 60 percent of all modules will incorporate

technology-enhanced learning elements, and every student will have access to

personalised learning pathways powered by adaptive learning technologies.

The digital learning transformation also encompasses accessibility. All digital

learning resources will comply with WCAG 2.1 AA standards, ensuring that

students with disabilities have equitable access. The university will establish

a dedicated Digital Pedagogy Unit staffed with instructional designers,

educational technologists, and accessibility specialists to support faculty

across all six faculties.

Key Performance Indicators

--------------------------

| KPI ID | KPI Description                              | Baseline (2024) | Target (2029) | Measurement Method                        |

|--------|----------------------------------------------|-----------------|---------------|-------------------------------------------|

| D1     | % of modules with tech-enhanced learning     | 25%             | 60%           | Annual module audit by Digital Pedagogy    |

| D2     | Student satisfaction with digital learning   | 3.2/5.0         | 4.3/5.0       | National Student Survey (NSS) Q21-Q23     |

| D3     | Staff completing digital skills training     | 15%             | 85%           | HR training records                       |

| D4     | Number of fully online programmes            | 4               | 18            | Programme registry                        |

| D5     | LMS daily active users                       | 6,200           | 14,500        | LMS analytics dashboard                   |

| D6     | WCAG 2.1 AA compliance rate for materials    | 40%             | 95%           | Accessibility audit tool reports          |

Timeline and Milestones

-----------------------

| Phase   | Period          | Milestone                                            |

|---------|-----------------|------------------------------------------------------|

| Phase 1 | Jan–Dec 2024    | Complete LMS procurement and pilot in 3 faculties     |

| Phase 2 | Jan–Jun 2025    | Launch Digital Skills Framework for all staff          |

| Phase 3 | Jul 2025–Jun 2026| Roll out adaptive learning in 30% of modules          |

| Phase 4 | Jul 2026–Dec 2027| Expand online programme portfolio to 12 programmes    |

| Phase 5 | Jan 2028–Dec 2029| Achieve 60% tech-enhanced modules and full compliance |

Responsible Parties

-------------------

- Lead: Pro-Vice-Chancellor (Education)

- Support: IT Services Director, Digital Pedagogy Unit Head

- Faculty Leads: Associate Deans (Learning & Teaching) in each faculty

- Budget Owner: Chief Financial Officer

================================================================================

STRATEGIC OBJECTIVE 2: RESEARCH EXCELLENCE AND INNOVATION

================================================================================

Description

-----------

GreenField University aims to strengthen its research profile by focusing on

interdisciplinary research themes with real-world impact. The university will

target increased funding from UK Research and Innovation (UKRI), Horizon Europe,

and industry partners. A new Research Impact Acceleration Fund will support the

translation of research outputs into societal and economic benefits.

Three flagship research centres will be established: the Centre for Sustainable

Energy Systems, the Centre for Health Informatics, and the Centre for Creative

Technologies. These centres will serve as hubs for collaborative,

interdisciplinary research, bringing together academics from multiple faculties

alongside external partners from industry, government, and the third sector.

The university will also focus on improving its REF (Research Excellence

Framework) performance. Currently, 45 percent of GreenField's research outputs

are rated as "internationally excellent" (3*) or "world-leading" (4*); the

target is to increase this to 65 percent by the next REF cycle. To achieve

this, the university will implement a structured mentorship programme for early-

career researchers, provide ring-fenced time for research activity, and

establish a peer review enhancement scheme.

The innovation agenda extends to knowledge exchange and enterprise. GreenField

will establish an Innovation Hub to support staff and student entrepreneurs,

providing access to seed funding, mentorship, co-working space, and

intellectual property advice. The target is to spin out at least eight new

ventures over the plan period.

Key Performance Indicators

--------------------------

| KPI ID | KPI Description                            | Baseline (2024) | Target (2029) | Measurement Method                     |

|--------|--------------------------------------------|-----------------|---------------|-----------------------------------------|

| R1     | Annual research funding secured (£M)       | £12.4M          | £25.0M        | Finance system (grants module)          |

| R2     | REF outputs rated 3* or 4*                 | 45%             | 65%           | Internal REF mock exercise              |

| R3     | Number of active research partnerships     | 38              | 80            | Research Office partnership database    |

| R4     | PhD completions per year                   | 95              | 160           | Registry records                        |

| R5     | Spin-out ventures created                  | 1               | 8 (cumulative)| Innovation Hub records                  |

| R6     | Research publications in top quartile      | 220             | 400           | Scopus/Web of Science analysis          |

Timeline and Milestones

-----------------------

| Phase   | Period          | Milestone                                            |

|---------|-----------------|------------------------------------------------------|

| Phase 1 | Jan–Sep 2024    | Establish three flagship research centres             |

| Phase 2 | Oct 2024–Jun 2025| Launch Innovation Hub and seed funding programme      |

| Phase 3 | Jul 2025–Dec 2026| Achieve £18M annual research funding                  |

| Phase 4 | Jan 2027–Dec 2028| Complete REF mock exercise and improvement programme  |

| Phase 5 | Jan–Dec 2029    | Deliver 65% 3*/4* outputs, 8 spin-outs cumulative    |

Responsible Parties

-------------------

- Lead: Pro-Vice-Chancellor (Research & Innovation)

- Support: Research Office Director, Innovation Hub Manager

- Faculty Leads: Associate Deans (Research) in each faculty

- Budget Owner: Chief Financial Officer

================================================================================

STRATEGIC OBJECTIVE 3: STUDENT EXPERIENCE AND WELLBEING

================================================================================

Description

-----------

A positive student experience is fundamental to GreenField University's success.

This objective focuses on creating a supportive, engaging, and holistic

university environment that promotes academic success, mental health, physical

wellbeing, and a strong sense of belonging. The university recognises that

student expectations are evolving — prospective students seek not just academic

quality but also a vibrant campus life, responsive support services, and a

genuine commitment to their personal development.

GreenField will introduce a comprehensive Student Wellbeing Strategy, expanding

the counselling service from 8 to 20 full-time equivalent (FTE) counsellors,

implementing a 24/7 digital mental health platform, and embedding wellbeing

check-ins within the personal tutor system. The target is to reduce student

counselling wait times from an average of 21 days to under 5 working days.

The university will also overhaul its student engagement strategy. A new Student

Voice Framework will ensure that student feedback systematically informs

decision-making at programme, faculty, and university levels. The Students'

Union will receive additional funding and support to expand societies, clubs,

and volunteering opportunities.

Campus infrastructure will be enhanced with a £15M investment in learning

spaces, including a new 24-hour study hub, refurbished library facilities, and

improved social spaces. A new Sports and Wellness Centre will open by 2027,

featuring a swimming pool, fitness studios, and an integrated wellbeing clinic.

Key Performance Indicators

--------------------------

| KPI ID | KPI Description                                | Baseline (2024) | Target (2029) | Measurement Method                     |

|--------|------------------------------------------------|-----------------|---------------|-----------------------------------------|

| S1     | Overall NSS satisfaction score                 | 76%             | 88%           | National Student Survey                 |

| S2     | Counselling service average wait time (days)   | 21              | 5             | Wellbeing service records               |

| S3     | Student retention rate (Year 1 to Year 2)      | 87%             | 94%           | Registry progression data               |

| S4     | Students participating in extracurricular      | 42%             | 70%           | Students' Union records                 |

| S5     | Graduate employability (within 15 months)      | 72%             | 88%           | Graduate Outcomes Survey                |

| S6     | Personal tutor meeting completion rate         | 60%             | 95%           | Tutor management system                 |

Timeline and Milestones

-----------------------

| Phase   | Period          | Milestone                                            |

|---------|-----------------|------------------------------------------------------|

| Phase 1 | Jan–Jun 2024    | Launch digital mental health platform                 |

| Phase 2 | Jul 2024–Mar 2025| Expand counselling team to 14 FTE                     |

| Phase 3 | Apr 2025–Dec 2025| Open 24-hour study hub, launch Student Voice Framework|

| Phase 4 | Jan 2026–Jun 2027| Complete Sports and Wellness Centre construction      |

| Phase 5 | Jul 2027–Dec 2029| Achieve 88% NSS satisfaction and 94% retention        |

Responsible Parties

-------------------

- Lead: Pro-Vice-Chancellor (Student Experience)

- Support: Director of Student Services, Students' Union President

- Faculty Leads: Associate Deans (Student Experience) in each faculty

- Budget Owner: Chief Financial Officer

================================================================================

STRATEGIC OBJECTIVE 4: INDUSTRY PARTNERSHIPS AND EMPLOYABILITY

================================================================================

Description

-----------

GreenField University is committed to producing graduates who are not only

academically accomplished but also career-ready and entrepreneurially minded.

This objective focuses on deepening industry engagement, expanding placement

and internship opportunities, integrating employability skills into the

curriculum, and establishing a robust employer advisory network.

The university will create an Industry Engagement Board comprising senior

leaders from at least 25 regional and national employers. This board will

advise on curriculum relevance, emerging skill needs, and collaborative

research opportunities. Every undergraduate programme will include a mandatory

work-related learning component (placement, internship, live project, or

consultancy) by 2027.

The Careers and Employability Service will be restructured and expanded, with

dedicated career coaches embedded within each faculty. A new Employer

Partnership Fund will provide matched funding for collaborative projects,

knowledge transfer partnerships (KTPs), and co-created modules.

An Entrepreneurship Academy will be launched to support student start-ups,

offering workshops, mentoring, pitch competitions, and access to seed funding.

The academy will work closely with the Innovation Hub (Strategic Objective 2)

to bridge academic research and commercial application.

Key Performance Indicators

--------------------------

| KPI ID | KPI Description                                  | Baseline (2024) | Target (2029) | Measurement Method                   |

|--------|--------------------------------------------------|-----------------|---------------|---------------------------------------|

| I1     | Graduate employment rate (15 months)             | 72%             | 88%           | Graduate Outcomes Survey              |

| I2     | Students completing work placements              | 35%             | 75%           | Placement office records              |

| I3     | Active industry partnerships                     | 45              | 120           | Industry Engagement Board records     |

| I4     | Employer satisfaction with graduates              | 3.5/5.0         | 4.5/5.0       | Annual employer survey                |

| I5     | Student start-ups launched                        | 8               | 35 (cumul.)   | Entrepreneurship Academy records      |

| I6     | KTPs and collaborative projects                   | 6               | 22            | Research & Enterprise Office records  |

Timeline and Milestones

-----------------------

| Phase   | Period          | Milestone                                            |

|---------|-----------------|------------------------------------------------------|

| Phase 1 | Jan–Jun 2024    | Establish Industry Engagement Board                   |

| Phase 2 | Jul 2024–Jun 2025| Launch Entrepreneurship Academy, embed career coaches |

| Phase 3 | Jul 2025–Dec 2026| Reach 60% placement participation                     |

| Phase 4 | Jan 2027–Dec 2028| Mandatory work-related learning in all UG programmes  |

| Phase 5 | Jan–Dec 2029    | Achieve 88% employment rate, 120 partnerships         |

Responsible Parties

-------------------

- Lead: Pro-Vice-Chancellor (Engagement & Partnerships)

- Support: Director of Careers & Employability, Entrepreneurship Academy Lead

- Faculty Leads: Programme Directors across all faculties

- Budget Owner: Chief Financial Officer

================================================================================

STRATEGIC OBJECTIVE 5: OPERATIONAL EFFICIENCY AND SUSTAINABILITY

================================================================================

Description

-----------

GreenField University is committed to becoming a carbon-neutral institution by

2035 and a financially resilient organisation through operational efficiency

improvements. This objective focuses on three pillars: environmental

sustainability, process optimisation, and financial health.

The university will implement a comprehensive Carbon Management Plan targeting

a 50 percent reduction in Scope 1 and Scope 2 emissions by 2029 (from a 2020

baseline). Key initiatives include transitioning the vehicle fleet to electric,

installing solar panels across campus buildings, upgrading heating systems to

heat pumps, and implementing a behaviour change programme for staff and

students.

Process optimisation will involve a major digital transformation of

administrative processes. An Enterprise Resource Planning (ERP) system will be

implemented to integrate finance, HR, procurement, and student records. Robotic

Process Automation (RPA) will be deployed for high-volume, repetitive tasks

such as invoice processing, enrolment verification, and timetabling.

Financial resilience will be strengthened through income diversification. The

university will grow international student recruitment (currently 18 percent

of the student body) to 28 percent, expand its portfolio of professional

development and executive education programmes, and increase philanthropic

income through an enhanced alumni engagement strategy.

Key Performance Indicators

--------------------------

| KPI ID | KPI Description                                | Baseline (2024) | Target (2029) | Measurement Method                     |

|--------|------------------------------------------------|-----------------|---------------|-----------------------------------------|

| O1     | Carbon emissions reduction (from 2020 base)   | 15%             | 50%           | Annual carbon audit (Scope 1 & 2)       |

| O2     | Administrative process automation rate         | 10%             | 45%           | IT Services automation log              |

| O3     | International student proportion               | 18%             | 28%           | Admissions data                         |

| O4     | Annual income from exec education (£M)         | £1.8M           | £6.5M         | Finance system                          |

| O5     | Staff satisfaction with admin processes         | 3.0/5.0         | 4.2/5.0       | Annual staff survey                     |

| O6     | Energy consumption reduction per m²            | Baseline year   | 30% reduction | Facilities management energy reports    |

Timeline and Milestones

-----------------------

| Phase   | Period          | Milestone                                            |

|---------|-----------------|------------------------------------------------------|

| Phase 1 | Jan–Dec 2024    | Complete carbon audit and publish Carbon Mgmt Plan    |

| Phase 2 | Jan–Dec 2025    | Begin ERP implementation, install solar on 4 buildings|

| Phase 3 | Jan–Dec 2026    | Launch executive education expansion programme        |

| Phase 4 | Jan–Dec 2027    | Complete ERP rollout, reach 25% international students|

| Phase 5 | Jan–Dec 2029    | Achieve 50% carbon reduction, 45% process automation  |

Responsible Parties

-------------------

- Lead: Chief Operating Officer

- Support: Director of Estates & Facilities, Director of Finance

- Faculty Leads: Faculty Managers

- Budget Owner: Chief Financial Officer

================================================================================

STRATEGIC OBJECTIVE 6: DIVERSITY, EQUITY AND INCLUSION

================================================================================

Description

-----------

GreenField University believes that diversity enriches the learning

environment, drives innovation, and reflects its civic responsibility. This

objective focuses on creating an institution where every student, staff member,

and community partner feels valued, respected, and empowered to succeed,

regardless of their background, identity, or circumstance.

The university will develop and implement a comprehensive Equality, Diversity

and Inclusion (EDI) Strategy, aligned with the Equality Act 2010 and the

university's commitment to the Race Equality Charter and Athena SWAN Charter.

Key priorities include closing attainment gaps between student demographic

groups, increasing the representation of underrepresented groups in senior

academic and professional services roles, and embedding inclusive practice into

all aspects of university life.

A dedicated EDI Office will be established, led by a Director of Equality,

Diversity and Inclusion reporting directly to the Vice-Chancellor. The office

will coordinate training programmes, monitor equality data, investigate

complaints, and advise on policy development. An annual EDI Report will be

published, providing transparent data on progress against targets.

Specific initiatives include: mandatory unconscious bias training for all staff

involved in recruitment and promotion decisions; a mentoring programme for

Black, Asian and Minority Ethnic (BAME) early-career academics; expansion of

the university's scholarship programme for students from low-participation

neighbourhoods; and development of a Disability Inclusion Framework to improve

the experience of disabled students and staff.

Key Performance Indicators

--------------------------

| KPI ID | KPI Description                                   | Baseline (2024) | Target (2029) | Measurement Method                  |

|--------|---------------------------------------------------|-----------------|---------------|---------------------------------------|

| E1     | BAME student attainment gap (good honours)        | 12 pp           | 4 pp          | Registry attainment data             |

| E2     | Women in senior academic roles (Prof/Reader)      | 32%             | 45%           | HR records                           |

| E3     | BAME staff in senior roles                         | 8%              | 18%           | HR records                           |

| E4     | Staff completing EDI training                      | 35%             | 90%           | HR training records                  |

| E5     | Students from low-participation neighbourhoods    | 14%             | 22%           | UCAS/Admissions data                 |

| E6     | Student satisfaction with inclusivity (NSS)        | 72%             | 88%           | National Student Survey              |

Timeline and Milestones

-----------------------

| Phase   | Period          | Milestone                                            |

|---------|-----------------|------------------------------------------------------|

| Phase 1 | Jan–Jun 2024    | Establish EDI Office, appoint Director of EDI         |

| Phase 2 | Jul 2024–Jun 2025| Launch Athena SWAN and Race Equality Charter actions  |

| Phase 3 | Jul 2025–Dec 2026| Roll out mandatory unconscious bias training          |

| Phase 4 | Jan 2027–Dec 2028| Expand scholarship programme, launch mentoring scheme |

| Phase 5 | Jan–Dec 2029    | Achieve attainment gap reduction and representation   |

Responsible Parties

-------------------

- Lead: Vice-Chancellor (personal oversight)

- Support: Director of EDI, Director of HR

- Faculty Leads: Faculty EDI Champions

- Budget Owner: Chief Financial Officer

================================================================================

GOVERNANCE AND REVIEW FRAMEWORK

================================================================================

The "Futures Forward" strategic plan will be governed by the following

structures and processes:

1. STRATEGIC PLAN OVERSIGHT BOARD

Chaired by the Vice-Chancellor, meeting quarterly. Membership includes all

Pro-Vice-Chancellors, the Chief Operating Officer, the Chief Financial

Officer, the Students' Union President, and two lay members of Council.

2. ANNUAL STRATEGIC REVIEW

Each October, the Oversight Board will conduct a comprehensive review of

progress against all KPIs. The review will include a traffic-light

assessment of each objective, an analysis of risks and emerging issues, and

recommendations for corrective actions.

3. MID-TERM STRATEGIC REFRESH (2027)

A substantive mid-term review will be conducted in 2027 to assess whether

the strategic objectives, KPIs, and timelines remain appropriate in light

of changes in the external environment (e.g., government policy, funding

landscape, technology developments).

4. KEY PERFORMANCE INDICATOR DASHBOARD

A live KPI dashboard will be maintained by the Strategy and Planning Office,

accessible to all senior leaders. The dashboard will display real-time or

near-real-time data for all KPIs, with drill-down capability by faculty,

department, and demographic group.

5. RISK MANAGEMENT

The university's Risk Register will be updated quarterly to reflect

strategic risks. Each strategic objective owner will maintain an objective-

level risk register, reviewed by the Oversight Board.

6. STAKEHOLDER ENGAGEMENT

The university will engage students, staff, alumni, and external partners

in the strategic plan through annual town halls, online consultation

platforms, and the Students' Union.

================================================================================

END OF STRATEGIC PLAN

================================================================================